## Schedule
Date | Phases | Tasks | Task Owner | Status
| Project Initiation and Planning | - Define project objectives, scope, and deliverables. | Rahat | In progress
- Establish communication channels between team members.
|  | - Identify hardware and software requirements. | Habib | Completed
|  | - Develop project plan and schedule. | Rahat | Completed
|  | - Habib: Design and develop hardware for monitoring battery voltage and temperature. | Habib | In progress
|  | - Habib: Assemble hardware and conduct initial tests. | Habib
|  | - Rahat: Develop client-side functionality for communication with the Transport server. | Rahat | In progress
|  | - Rahat: Implement cellular modem, Wi-Fi, and Ethernet communication. | Rahat
|  | - Rahat: Integrate battery monitoring with server communication. | Rahat
|  | - Habib & Rahat: Develop control system code for lights and annulus. | Habib & Rahat | Not started
|  | - Habib & Rahat: Integrate control system with industrial PC. | Habib & Rahat
|  | - Habib & Rahat: Perform extensive testing and bug fixing. | Habib & Rahat
|  | - Prepare comprehensive documentation and user manual. | Rahat
|  | - Conduct final demonstration and presentation. | Rahat